## Risk Register
RISK REGISTER — Healthcare Program Management
Kaylee Gassen, Program Manager · Track, assess, and mitigate project risks
Risk ID | Risk Description | Category | Likelihood (1–5) | Impact (1–5) | Risk Score (L×I) | Risk Level | Mitigation Strategy | Owner
R-001 | Staff turnover disrupts program continuity and scheduling | HR / People | 3 | 4 |  | HIGH | Cross-train 2+ staff per role; maintain documented SOPs | Program Manager
R-002 | Regulatory changes impact documentation requirements | Compliance | 2 | 5 |  | HIGH | Monitor ASAM/state updates monthly; review compliance calendar | Compliance Officer
R-003 | Budget variance exceeds 10% of program allocation | Financial | 2 | 4 |  | MEDIUM | Monthly budget reviews; escalate at 5% variance | Operations Director
R-004 | EMR system downtime disrupts case documentation | Technology | 2 | 3 |  | MEDIUM | Maintain paper backup protocol; IT escalation path documented | IT Lead
R-005 | Client-to-staff ratio exceeds safe threshold | Operations | 2 | 4 |  | MEDIUM | Trigger alert at 90% capacity; pre-approved temp staff roster | Program Manager
R-006 | External provider delays affect service delivery | Vendor | 3 | 3 |  | MEDIUM | Dual-vendor agreements; 30-day notice contract clause | Operations Director
R-007 | Accreditation audit finds documentation gaps | Compliance | 1 | 5 |  | LOW-MED | Quarterly internal audits; real-time EMR compliance tracking | Compliance Officer
R-008 | Stakeholder misalignment delays program decisions | Governance | 2 | 3 |  | MEDIUM | Weekly stakeholder updates; RACI matrix enforced | Program Manager
RISK SCORE LEGEND
1–4 | LOW
5–9 | MEDIUM
10–25 | HIGH